## A Sites
Committed and Proposed Housing Sites Category A Sites
Local Plan Reference | Application Number | Site Name | Settlement | Type of application | Site Area (hectares) | Total Number of dwellings | Remaining Dwelling capacity as of 1st April 2022 | 2022-2023* | 2023-2024 | 2024-2025 | 2025-2026 | 2026-2027 | Five year completions | Notes
H1C-1 | PA/2011/0941 and PA/2014/1183 | Plot 29 Hebden Road | Scunthorpe | Outline and Reserved Matters | 0.48 | 14 | 14 | 0 | 0 | 0 | 0 | 7 | 7 | Planning permission has been implemented.
H1C-4 | PA/2017/1483 | Methodist Church Fordingham Road | Scunthorpe | Full | 0.12 | 14 | 14 | 0 | 0 | 0 | 7 | 7 | 14 | Planning permission has been implemented. Application to discharge conditions has been received by the council.
H1C-5 | PA/2018/664 | Land at 1-3 Cliff Gardens | Scunthorpe | Full | 0.2 | 10 | 10 | 0 | 10 | 0 | 0 | 0 | 10 | Development commenced and expected to be completed 2023/2024.
H1C-6 | PA/2019/1088 | Lakeside (Land west of Turnstone Drive) | Scunthorpe | Full | 2.38 | 88 | 88 | 42 | 30 | 16 | 0 | 0 | 88 | Development commenced.
H1C-6 | PA/2019/1107 | Lakeside (Land west of Dunlin Drive | Scunthorpe | Full | 3.11 | 122 | 122 | 24 | 30 | 30 | 30 | 8 | 122 | Development commenced.
H1C-7 | PA/2018/838 | Land south of Ashby Turn Primary Care Centre, The Link | Scunthorpe | Full | 0.26 | 18 | 18 | 7 | 11 | 0 | 0 | 0 | 18 | Development commenced.
H1C-9 | PA/2017/1399 and PA/2020/872 | Land at Bottesford Road | Scunthorpe | Outline and Reserved Matters | 0.16 | 10 | 10 | 10 | 0 | 0 | 0 | 0 | 0 | Development completed 2022/2023.
H1C-11 | PA/2017/2137 | Land off Burringham Road (Roman Way) | Scunthorpe | Full | 2.49 | 85 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | Development completed 2022/2023.
H1C-13 | PA/2018/2404 | Land at Dartmouth Road | Scunthorpe | Full | 2.49 | 77 | 53 | 41 | 12 | 0 | 0 | 0 | 53 | Development commenced, 24 dwellings completed in 2021/2022.
H1C-14 | PA/2014/1426 and PA/2019/1260 | Land Rear of 38 & 40 Ville Road | Scunthorpe | Outline and Reserved Matters | 0.12 | 5 | 5 | 5 | 0 | 0 | 0 | 0 | 5 | Development completed 2022/202.
H1C-15 | PA/2019/1180 | 22-24 Cole Street | Scunthorpe | Full | 0.04 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | Development commenced.
H1C-22 | PA/2019/1714 | 50 The Riveter Henderson Avenue | Scunthorpe | Full | 0.03 | 6 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | Development commenced and expected to be completed 2022/2023.
H1P-1 | PA/2020/2049 | Land at Phoenix Parkway Phase 1 | Scunthorpe | Full | 7.96 | 158 | 158 | 0 | 30 | 30 | 30 | 30 | 120 | Development commenced.
H1C-23 | PA/2018/1049 | Land to the rear of 13-19 Pasture Road | Barton Upon Humber | Full | 0.35 | 16 | 16 | 7 | 9 | 0 | 0 | 0 | 16 | Development commenced.
H1C-24 | PA/2016/1763 | Coach and Horses Inn 86 - 88 High Street, Barton | Barton Upon Humber | Full | 0.34 | 17 | 12 | 2 | 8 | 2 | 0 | 0 | 12 | Development commenced.
HC1-25 | PA/2020/1612 | Land Adjacent to White Swan Butts Road | Barton Upon Humber | Full | 0.15 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 5 | Development commenced.
H1P-12 | PA/2020/1628 | Pasture Road South | Barton Upon Humber | Full | 21.4 | 317 | 317 | 0 | 20 | 30 | 30 | 30 | 110 | The site is in ownership of a house builder who has built out the 4 previous phases of the site. Various conditions have been submitted and discharged.
H1C-26 | PA/2014/0887 | Island Carr | Brigg | Outline and Reserved Matters | 1.88 | 60 | 60 | 0 | 0 | 10 | 25 | 25 | 60 | Development commenced.
H1C-27 | PA/2017/1234 | Falcon Cycles, Bridge Street, Brigg, Phase 1 | Brigg | Full | 2.2 | 67 | 67 | 17 | 25 | 25 | 0 | 0 | 67 | Development commenced.
H1C-28 | PA/2021/288 | Falcon Cycles, Bridge Street, Brigg, Phase 2 | Brigg | Outline and Reserved Matters | 0.18 | 20 | 20 | 0 | 20 | 0 | 0 | 0 | 20 | Development commenced.
H1C-29 | PA/2004/0692 | Silversides Lane | Brigg | Reserved Matters | 1.57 | 44 | 44 | 0 | 0 | 0 | 0 | 20 | 20 | Planning application has been implemented. Proforma received confirming the site is being sold to a housebuilder.
H1C-30 | PA/2017/1652 | 6 Market Place | Brigg | Full | 0.21 | 14 | 14 | 0 | 0 | 10 | 4 | 0 | 14 | Planning permission implemented.
H1C-32 | PA/2019/1454 and PA/2021/1968 | Victoria Road | Barnetby | Full | 0.97 | 27 | 27 | 20 | 7 | 0 | 0 | 0 | 27 | Development commenced.
H1C-34 | PA/2020/603 and PA/2021/541 | Land off Ferry Road/Chestnut Rise | Barrow Upon Humber | Outline and Reserved Matters | 3.05 | 64 | 64 | 0 | 25 | 25 | 14 | 0 | 64 | Development commenced.
H1C-35 | PA/2020/803 | Land north of Ferry Road East | Barrow Upon Humber | Full | 0.56 | 9 | 9 | 9 | 0 | 0 | 0 | 0 | 0 | Development completed 2022/2023.
H1C-37 | PA/2017/124 | The Red Lion | Broughton | Full | 0.35 | 6 | 6 | 6 | 0 | 0 | 0 | 0 | 0 | Development completed 2022/2023.
H1C-39 | PA/2017/1975 and PA/2020/1413 | Westgate Road | Belton | Outline and Reserved Matters | 0.9 | 23 | 23 | 10 | 13 | 0 | 0 | 0 | 23 | Development commenced.
H1C-41 | PA/2019/849 | Land adjacent 1 Belgrave Close | Belton | Full | 0.18 | 5 | 5 | 0 | 0 | 5 | 0 | 0 | 5
H1C-42 | PA/2018/660 and PA/2019/1828 | Belton Garden Centre Sandtoft Road | Belton | Outline and Reserved Matters | 0.34 | 5 | 5 | 0 | 5 | 0 | 0 | 0 | 0 | Development commenced.
H1C-45 | PA/2017/1929 | 3a-8 Harris View | Epworth | Full | 0.14 | 7 | 7 | 0 | 7 | 0 | 0 | 0 | 7 | Development commenced.
H1C-46 | PA/2019/1804 | The Sycamores Battle Green | Epworth | Full | 0.11 | 5 | 5 | 4 | 1 | 0 | 0 | 0 | 5 | Development commenced.
HC1-47 | PA/2018/1581 and PA/2022/54 | Land off Howe Lane and Hawthorne Gardens | Goxhill | Outline and Reserved Matters | 3.35 | 84 | 84 | 0 | 0 | 20 | 20 | 20 | 60 | Outline, reserved matters and various conditions discharged. The site is owned by a local house builder.
HC1-48 | PA/2019/841 | Land east of Strathdee, Barrow Road | Goxhill | Outline | 0.36 | 9 | 9 | 0 | 4 | 5 | 0 | 0 | 9
HC1-50 | PA/2019/842 | Land north of 6 Thornton Road | Goxhill | Outline | 0.34 | 8 | 8 | 0 | 0 | 8 | 0 | 0 | 8
H1C-51 | PA/2020/538 | Conway Thornton Road | Goxhill | Full | 0.83 | 6 | 6 | 0 | 0 | 3 | 3 | 0 | 6
H1C-53 | PA/2018/1716 and PA/2021/1210 | Land to the West of Station Road | Hibaldstow | Outline and reserved matters | 2.2 | 48 | 48 | 0 | 24 | 24 | 0 | 0 | 48 | Various conditions have been discharged by the developer.
H1C-54 | PA/2019/996 | Brook House Farm, Church Street | Hibaldstow | Full | 0.61 | 14 | 10 | 1 | 5 | 4 | 0 | 0 | 10 | Development commenced.
H1C-55 | PA/2020/158 and PA/2021/657 | Land north of Wheelgates, Brigg Road, Hibaldstow, | Hibaldstow | Outline and Reserved Matters | 0.47 | 5 | 5 | 0 | 2 | 3 | 0 | 0 | 5 | Site owned by developer.
H1C-57 | PA/2017/389 | Land west of Station Road | Kirton In Lindsey | Full | 2.91 | 91 | 91 | 29 | 47 | 15 | 0 | 0 | 91 | Development commenced.
H1C-58 | PA/1999/0920 | North of Spa Hill | Kirton In Lindsey | Full | 6.5 | 102 | 40 | 0 | 10 | 10 | 10 | 10 | 40 | Development commenced.
H1C-60 | PA/2020/1869 | 13 High Street | Kirton In Lindsey | Full | 0.08 | 6 | 6 | 0 | 0 | 6 | 0 | 0 | 6
H1C-63 | PA/2015/1390 and PA/2019/1336 | Land to the rear of North Street and Cemetery Road, | Winterton | Outline and Reserved Matters | 6.62 | 135 | 135 | 0 | 25 | 25 | 25 | 25 | 100 | Development commenced.
H1C-64 | PA/2020/324 | Land at Top Road | Winterton | Full | 2.9 | 110 | 90 | 39 | 30 | 21 | 0 | 0 | 90 | Development commenced.
H1C-65 | PA/2018/1759 | Land south of Coates Avenue | Winterton | Full | 1.47 | 40 | 40 | 0 | 40 | 0 | 0 | 0 | 40 | Development commenced.
H1C-66 | PA/2019/1497 | 5 Northlands Road | Winterton | Outline and Reserved Matters | 0.41 | 5 | 5 | 0 | 0 | 0 | 0 | 5 | 5 | PA/2022/1872 Reserved Matters granted 31/1/2023
H1C-67 | PA/2017/2080 | Land north of Front Street, Ulceby | Ulceby | Full | 0.97 | 14 | 10 | 9 | 1 | 0 | 0 | 0 | 10 | Development commenced.
H1C-68 | PA/2017/1450 | Land rear of new convenience store, off Church Lane, Ulceby | Ulceby | Full | 0.61 | 9 | 9 | 6 | 3 | 0 | 0 | 0 | 9 | Development commenced.
H1C-71 | PA/2020/794 | Land at Risehome Spruce Lane | Ulceby | Full | 0.38 | 8 | 8 | 1 | 4 | 3 | 0 | 0 | 8 | Development commenced.
H1C-72 | PA/2013/1256 | 7 Lakes Industrial Estate, Crowle Wharf | Ealand | Outline and Reserved | 0.61 | 17 | 17 | 6 | 8 | 3 | 0 | 0 | 17 | Development commenced.
H1C-73 | PA/2015/0481 | 7 Lakes Industrial Estate, Crowle Wharf | Ealand | Outline and Reserved | 0.75 | 9 | 5 | 5 | 0 | 0 | 0 | 0 | 5 | Development completed 2022/2023
HC1-74 | PA/2021/276 | Old Railway Sidings, A18 from Althorpe to Gunness | Keadby | Outline and Reserved | 0.52 | 14 | 14 | 0 | 0 | 0 | 7 | 7 | 14
HC1-76 | PA/2018/1884 | West Street | Scawby | Full | 0.6 | 8 | 1 | 1 | 0 | 0 | 0 | 0 | 1 | Development completed 2022/2023
HC1-77 | PA/2018/1718 | Land adjacent to Ridgeway House Mill Lane | Wrawby | Full | 0.41 | 8 | 8 | 0 | 8 | 0 | 0 | 0 | 8 | Development commenced.
HC1-78 | PA/2017/0674 and PA/2022/1307 | Land off Applefields | Wrawby | Outline and reserved matters | 1.78 | 22 | 22 | 0 | 0 | 0 | 8 | 8 | 0 | Site owned by developer.
Total | [7 empty] | 311 | 487 | 333 | 213 | 202 | 1491
*2022-23 is actual completions